## Week 2
problems
具体要做什么？或者说背景是什么？
有什么需要注意的地方？
可能要用到什么技术，需要做什么准备？
以后的安排如何？是不是每周见一次面？
有没有什么好的建议？或者教授的想法是什么？
我的想法是做一个类似ar的地图，有没有问题？
什么样的人会用这个app？
室内信息展示为什么需要用到ar呢？
优势是什么?可以加入其它技术吗？
如果真的要用来展示信息的话，有什么东西可以实时反映并且监控室内的信息呢？

## weeek3
title | xxx
background | nowadays, there many big malls in a city, within which lots of supermarkets or shops are selling products.
domain | smart living
problem | people spend lots of time on shopping if they are not fimiliar with a mall, a shop or a product
remarks | workers in mall often hang signs on ceiling to navigate vistors to some functional places, e.g. toilet.
project aims | obtain useful imformation in a short time when shopping in a mall

## week8
tasks | objectives |  | 2018-10-26 | 2018-10-27 | 2018-10-28
study ARCore | ARCore functions | 8 | 8 | 8 | 8
| android basic knowledge | 8 | 8 | 8 | 7
study OpenCV |  | 8 | 7 | 6 | 8
design GUI | design init GUI | 1 | 0 | 0 | 0
| implement GUI | 8 | 8 | 8 | 8
| estimated hours | 33
| remaining effort | 33 | 31 | 30 | 31

## week9
tasks | objectives |  | 2018-10-29 | 2018-10-30 | 2018-10-31 | 2018-11-01 | 2018-11-02 | 2018-11-03 | 2018-11-04
study ARCore | ARCore functions | 8 | 8 | 8 | 8 | 6 | 6 | 5 | 4
| android basic knowledge | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| acknowledge | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
study OpenCV |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
design GUI | design init GUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| implement GUI | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| estimated hours | 35
| remaining effort | 35

## week10
tasks | objectives |  | 2018-11-04 | 2018-11-05 | 2018-11-06 | 2018-11-07 | 2018-11-08 | 2018-11-09 | 2018-11-10
study ARCore | ARCore functions | 8 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| android basic knowledge | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 5
| OpenGL acknowledge | 8 | 8 | 8 | 8 | 8 | 7 | 6 | 5
study OpenCV |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
design GUI | design init GUI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| implement GUI | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| estimated hours | 39
| remaining effort | 39 | 35 | 35 | 35 | 35 | 34 | 31 | 30